## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Milestone 1 | Milestone 1 | US-01 | As a user, I want to submit a question, AI response and optional reference answer for evaluation. | Must | Evaluation input | Bindu Priya | Completed
Milestone 1 | Milestone 1 | US-02 | As a system, I want relevant knowledge retrieved from a reference knowledge base for grounded evaluation. | Must | RAG pipeline | Bindu Priya | Completed
Milestone 1 | Milestone 1 | US-03 | As a developer, I want a defined multi-agent architecture, scoring dimensions and evaluation workflow. | Must | System design | Bindu Priya | Completed
Milestone 2 | Milestone 2 | US-04 | As a user, I want a Relevance Agent to score how directly the AI response answers the question. | Must | US-01, RAG | Bindu Priya | Completed
Milestone 2 | Milestone 2 | US-05 | As a user, I want an Accuracy Agent to evaluate factual support using retrieved evidence. | Must | US-02 | Bindu Priya | Completed
Milestone 2 | Milestone 2 | US-06 | As a user, I want hallucinated or unsupported claims to be identified and reported. | Must | US-02, US-05 | Bindu Priya | Completed
Milestone 3 | Milestone 3 | US-07 | As a user, I want Completeness scoring to identify missing aspects of an answer. | Must | Evaluation pipeline | Bindu Priya | Completed
Milestone 3 | Milestone 3 | US-08 | As a user, I want a Verdict Agent to combine relevance, accuracy, hallucination and completeness scores into Pass, Needs Improvement or Fail. | Must | US-04 to US-07 | Bindu Priya | Completed
Milestone 3 | Milestone 3 | US-09 | As a user, I want a results interface showing dimension scores, reasoning, findings and final verdict. | Must | US-04 to US-08 | Bindu Priya | Completed
Milestone 3 | Milestone 3 | US-10 | As a user, I want to upload a CSV and evaluate multiple question-response pairs automatically. | Must | Evaluation pipeline | Bindu Priya | Completed
Milestone 4 | Milestone 4 | US-11 | As a user, I want dashboard analytics and charts to understand batch evaluation quality and trends. | Must | US-10 | Bindu Priya | Completed
Milestone 4 | Milestone 4 | US-12 | As a user, I want structured batch evaluation results exported as a PDF report. | Must | US-10, US-11 | Bindu Priya | Completed
Milestone 4 | Milestone 4 | US-13 | As a developer, I want end-to-end validation of single and batch evaluation workflows, including invalid-input handling and scoring consistency. | Must | All modules | Bindu Priya | Completed
Milestone 4 | Milestone 4 | US-14 | As a stakeholder, I want technical documentation, project report and final demonstration material covering evaluation of at least two distinct AI systems. | Should | Completed system | Bindu Priya | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate | Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30 | Day 31 | Day 32 | Day 33 | Day 34 | Day 35 | Day 36 | Day 37 | Day 38 | Day 39 | Day 40 | Day 41 | Day 42 | Day 43 | Day 44 | Day 45 | Day 46 | Day 47 | Day 48 | Day 49 | Day 50 | Day 51 | Day 52
US-01 | M1-T01 | Study AI response evaluation, hallucination detection, RAG and evaluation frameworks | 30-Jun-2026 | 02-Jul-2026 | Bindu Priya | Research | Completed | 6 | 6 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | M1-T02 | Design architecture, agent responsibilities, scoring dimensions and data flow | 01-Jul-2026 | 04-Jul-2026 | Bindu Priya | System Design | Completed | 8 | 8 | 0 | 1 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | M1-T03 | Implement evaluation input workflow for question, response and optional reference | 03-Jul-2026 | 06-Jul-2026 | Bindu Priya | Implementation | Completed | 8 | 8 | 0 | 0 | 0 | 1 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | M1-T04 | Prepare TruthfulQA/SQuAD knowledge sources, embeddings and ChromaDB retrieval index | 04-Jul-2026 | 08-Jul-2026 | Bindu Priya | RAG Development | Completed | 12 | 12 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | M1-T05 | Validate retrieval and finalize Milestone 1 integration | 08-Jul-2026 | 09-Jul-2026 | Bindu Priya | Validation | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | M2-T01 | Implement Relevance Agent using embedding similarity and explanatory reason | 10-Jul-2026 | 14-Jul-2026 | Bindu Priya | Agent Development | Completed | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | M2-T02 | Implement Accuracy Agent with retrieved evidence and score thresholds | 13-Jul-2026 | 17-Jul-2026 | Bindu Priya | Agent Development | Completed | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | M2-T03 | Implement Hallucination Detection Agent using retrieved context and unsupported-claim reporting | 15-Jul-2026 | 19-Jul-2026 | Bindu Priya | Agent Development | Completed | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | M2-T04 | Validate Relevance, Accuracy and Hallucination agents on varied question-response pairs | 18-Jul-2026 | 21-Jul-2026 | Bindu Priya | Validation | Completed | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | M3-T01 | Implement Completeness Agent to score coverage and identify missing points | 22-Jul-2026 | 25-Jul-2026 | Bindu Priya | Agent Development | Completed | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | M3-T02 | Implement Verdict Agent with overall score and Pass/Needs Improvement/Fail thresholds | 24-Jul-2026 | 28-Jul-2026 | Bindu Priya | Agent Development | Completed | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | M3-T03 | Develop per-dimension results interface with scores, reasons and verdict | 26-Jul-2026 | 29-Jul-2026 | Bindu Priya | UI Development | Completed | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | M3-T04 | Implement CSV batch evaluation, aggregation, metadata handling and result storage | 27-Jul-2026 | 31-Jul-2026 | Bindu Priya | Batch Processing | Completed | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | M4-T01 | Build evaluation scoring dashboard with summary cards, verdict distribution and quality charts | 01-Aug-2026 | 05-Aug-2026 | Bindu Priya | Dashboard | Completed | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | M4-T02 | Implement ReportLab PDF report generation and report download endpoint | 04-Aug-2026 | 07-Aug-2026 | Bindu Priya | Report Generation | Completed | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | M4-T03 | Conduct end-to-end testing for single evaluation, batch CSV, dashboard, RAG, agents, verdicts and errors | 07-Aug-2026 | 11-Aug-2026 | Bindu Priya | Testing | Completed | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | M4-T04 | Prepare technical documentation, project report and demonstration material for two AI-system examples | 09-Aug-2026 | 13-Aug-2026 | Bindu Priya | Documentation | Completed | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | M4-T05 | Final refinement of documentation, Agile artifacts, screenshots and demonstration readiness | 14-Aug-2026 | 20-Aug-2026 | Bindu Priya | Finalization | Completed | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 2 | 2 | 2

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Milestone 1 | 02-Jul-2026 | Architecture and research artifacts needed alignment with the implementation scope. | Consolidated system design, agent responsibilities, scoring dimensions and technology choices.
Milestone 1 | 03-Jul-2026 | Initial input flow had to support question, AI response and optional reference data. | Implemented and validated the evaluation input workflow.
Milestone 1 | 07-Jul-2026 | Grounding required a reusable knowledge base for evaluation agents. | Prepared TruthfulQA/SQuAD data, embeddings and ChromaDB retrieval.
Milestone 1 | 09-Jul-2026 | RAG retrieval needed validation before agent development could continue. | Validated retrieval results and completed Milestone 1 integration.
Milestone 2 | 14-Jul-2026 | Individual evaluation required live agent scores instead of placeholder values. | Integrated the Relevance Agent into the evaluation pipeline.
Milestone 2 | 16-Jul-2026 | Accuracy evaluation needed evidence from retrieved context. | Integrated Accuracy scoring with retrieved knowledge and evidence messages.
Milestone 2 | 18-Jul-2026 | Hallucination detection needed explicit unsupported-claim reporting. | Implemented similarity-based hallucination detection and status reporting.
Milestone 2 | 20-Jul-2026 | Agent validation needed broader examples than ideal responses. | Expanded validation across varied question-response pairs.
Milestone 3 | 24-Jul-2026 | Completeness and final verdict were required for end-to-end scoring. | Added Completeness scoring and Verdict aggregation.
Milestone 3 | 28-Jul-2026 | Users needed readable per-dimension scores and explanations. | Completed results interface for scores, reasons and final verdict.
Milestone 3 | 31-Jul-2026 | Batch evaluation needed robust CSV handling and aggregate results. | Implemented CSV batch processing, metadata fields and summary calculations.
Milestone 4 | 05-Aug-2026 | Batch results needed analytics rather than only row-level outputs. | Completed dashboard cards, verdict distribution and quality-trend presentation.
Milestone 4 | 07-Aug-2026 | Batch results needed a structured export mechanism. | Integrated ReportLab PDF generation and report download.
Milestone 4 | 11-Aug-2026 | The complete pipeline required systematic functional and error-handling validation. | Executed end-to-end tests covering single, batch, dashboard, RAG, scoring and invalid-input cases.
Milestone 4 | 13-Aug-2026 | Final deliverables had to reflect the completed FastAPI + React implementation. | Finalized technical documentation, project report and demonstration material.
Milestone 4 | 14-Aug-2026 | Agile artifacts required consistency with the implemented project. | Reviewed and refined backlog, sprint tasks, defects, testing and retrospectives.
Milestone 4 | 18-Aug-2026 | Final artifacts required consistency across implementation, screenshots and documentation. | Cross-checked repository structure, screenshots, report content and Agile documentation.
Milestone 4 | 20-Aug-2026 | Final submission package required a last consistency check. | Complete final review and prepare the project demonstration/submission package.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Milestone 1 | 30-Jun-2026 | 09-Jul-2026 | Bindu Priya | Validate architecture decisions early with small prototypes. | Avoid extending research before implementation feedback. | Keep modular agents and RAG grounding central. | Use prototype feedback to refine the architecture and data flow.
2 | Milestone 2 | 10-Jul-2026 | 21-Jul-2026 | Bindu Priya | Add structured validation cases while building each agent. | Avoid testing only ideal responses. | Keep agent outputs explicit and explainable. | Expand evaluation examples across different question-answer types.
3 | Milestone 3 | 22-Jul-2026 | 31-Jul-2026 | Bindu Priya | Design UI and aggregation together for consistency. | Avoid redundant summaries in result views. | Keep dimension scores separate from the final verdict. | Keep Verdict Agent responsible for final consolidation.
4 | Milestone 4 | 01-Aug-2026 | 13-Aug-2026 | Bindu Priya | Plan documentation, testing and reporting alongside feature work. | Avoid leaving all documentation and testing until the end. | Keep dashboard, reporting and testing aligned with the evaluation pipeline. | Finalize technical documentation, report and demo material alongside implementation.
5 | Milestone 4 | 14-Aug-2026 | 20-Aug-2026 | Bindu Priya | Cross-check Agile artifacts against the final repository before submission. | Avoid inconsistencies between screenshots, code and documentation. | Keep final validation and demonstration preparation structured. | Perform a final consistency review and prepare the submission package.

## Defects
Defect ID | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
D-001 | Initial evaluation flow required robust validation for missing or empty question/response values. | Milestone 1 | Bindu Priya | Validation / Input | Added request validation and tested empty question and response handling. | 06-Jul-2026 | Closed | Invalid input cases are handled without normal evaluation.
D-002 | RAG retrieval required a persistent ChromaDB knowledge base before accuracy and hallucination scoring could be grounded. | Milestone 1 | Bindu Priya | Integration | Built the knowledge base from TruthfulQA and SQuAD and connected the retriever. | 08-Jul-2026 | Closed | Retriever returns relevant context for evaluation.
D-003 | Agent outputs needed consistent score keys and defensive handling when evidence was unavailable. | Milestone 2 | Bindu Priya | Robustness | Standardized result dictionaries and added fallback messages for missing retrieved context. | 19-Jul-2026 | Closed | Evaluation pipeline remains stable when evidence is unavailable.
D-004 | Batch evaluation required validation of required CSV columns and safe handling of blank rows. | Milestone 3 | Bindu Priya | Batch Processing | Added required-column checks and skipped invalid blank question-response rows. | 31-Jul-2026 | Closed | Valid CSV files are processed and invalid structure raises a clear error.
D-005 | Dashboard and PDF reporting required a complete batch-result summary rather than only row-level outputs. | Milestone 4 | Bindu Priya | Feature Integration | Integrated batch summaries, dashboard analytics, verdict distribution and ReportLab PDF generation. | 13-Aug-2026 | Closed | Batch results are available for analytics and structured PDF export.
D-006 | Final submission artifacts required consistency across test evidence, screenshots, report and Agile documentation. | Milestone 4 | Bindu Priya | Documentation | Cross-checked implementation, screenshots, test results, project report and Agile sheets before finalization. | 18-Aug-2026 | Closed | Final artifacts are aligned with the implemented FastAPI + React project.

## Unit Test Plan
Sl: No: | Test Case Name | Test Procedure | Condition to be tested | Expected Result | Actual Result
1 | Input validation | Submit a valid question and AI response through the evaluation interface. | Required question and response are provided. | Input is accepted and evaluation starts. | Passed
2 | Empty question handling | Submit an empty question. | Question field is blank. | System handles invalid input without normal evaluation. | Passed
3 | Empty response handling | Submit an empty AI response. | Response field is blank. | System handles invalid input without normal evaluation. | Passed
4 | Reference/RAG handling | Run evaluation with and without reference grounding. | Reference is optional and retrieval is available. | Reference is used when supplied; otherwise RAG retrieval provides grounding context. | Passed
5 | Relevance agent | Evaluate a question-response pair for relevance. | Valid question and response are supplied. | Relevance score and reason are generated. | Passed
6 | Accuracy agent | Evaluate factual support using retrieved evidence. | Reference or relevant retrieved evidence is available. | Accuracy score, evidence and retrieved context are generated. | Passed
7 | Hallucination detection | Evaluate a response containing unsupported information. | Grounding evidence is available. | Unsupported or potentially hallucinated information is identified and reported. | Passed
8 | Completeness agent | Evaluate a response that omits requested aspects. | Question contains multiple expected aspects. | Completeness score and missing points are generated. | Passed
9 | Verdict aggregation | Run the complete judge pipeline. | Dimension scores are available. | Overall score and Pass/Needs Improvement/Fail verdict are generated. | Passed
10 | Batch CSV validation | Upload a CSV containing question and response columns. | Required CSV columns are present. | Rows are accepted for batch processing. | Passed
11 | Batch evaluation | Process multiple question-response pairs. | Valid batch dataset is uploaded. | Rows are evaluated and aggregate results are generated. | Passed
12 | Dashboard analytics | Open dashboard after batch evaluation. | Batch results are available. | Summary cards, charts and verdict distribution are displayed. | Passed
13 | PDF report export | Download the report after a completed batch run. | Batch results are available. | A structured PDF report is generated and downloaded. | Passed
14 | End-to-end pipeline | Execute the complete single and batch evaluation workflow. | All modules are available. | Full workflow completes successfully from input to report. | Passed
15 | Scoring consistency | Run the same evaluation dataset multiple times and compare dimension scores and verdicts. | Same inputs and same evaluation configuration are used. | Scores and verdicts remain consistent across repeated runs. | Passed